## SCRUM Storyboard
Committed Backlog Items | Tasks not started | Tasks in Progress | Tasks Completed | Note: | To see descriptions of each task, see the "Task Descriptions" page
Input Multiple Files | OPL Multiple Input Files Coding
IR Multiple Input Files Coding
OPL Multiple Input Files Testing
IR Multiple Input Files Testing
IRV Candidate Rankings Filled in Ballot | Invalid Ballots Coding
Invalid Ballots Testing
PO Algorithm CSV Input | PO CSV Input Coding
PO CSV Input Testing
Invalidated Ballots File | Invalidated Ballots File Coding
Invalidated Ballots File Testing

## Task Descriptions
Unique Task Name: | OPL Multiple Input Files Coding
Associated User Story: | Input Multiples Files
Short Description: | Read in mulitple OPL CSV files for the same election
Additional Notes: | Will update the current code in the CreateElection class
Assumptions: | All the headers are the same for each input file The extra CSV files also come in as a CSV file
Acceptance Criteria: | Multiple CSV files should be able to be inserted into the ballot file Each CSV file can be inserted in any order Each CSV file is processed
Assigned Person(s): | Michael
Unique Task Name: | IR Multiple Input Files Coding
Associated User Story: | Input Multiples Files
Short Description: | Read in multiple IR files and run election
Additional Notes: | Need to update currently avalible code
Assumptions: | All Headers are the same
Acceptance Criteria: | Can proccess multiple IR files csv to be run in a single election Each CSV file can be inserted in any order
Assigned Person(s): | Jack Foley
Unique Task Name: | OPL Multiple Input Files Testing
Associated User Story: | Input Multiples Files
Short Description: | Test that the OPL instance created includes all the ballots from each input file
Additional Notes: | Adding unit tests to CreateElection unit test file
Assumptions: | N/A
Acceptance Criteria: | The associated test logs are created The tests are automatically run to determine whether the multiple input files code works
Assigned Person(s): | Michael
Unique Task Name: | IR Multiple Input Files Testing
Associated User Story: | Input Multiples Files
Short Description: | Test that the IR instace created includes all the ballots from each input file
Additional Notes: | Adding Unit test to CreateElection unit test file
Assumptions: | Test ballots exist
Acceptance Criteria: | The associated test logs are created The tests are automatically run to determine whether the multiple input files code works All unit tests previously reated to reading ballot files in IR pass
Assigned Person(s): | Jack Foley
Unique Task Name: | Invalid Ballots Coding
Associated User Story: | IRV Candidate Rankings Filled in Ballot
Short Description: | Ballots that have less than half of the ballots ranked are invalidated and not considered in the election.
Additional Notes: | None
Assumptions: | None
Acceptance Criteria: | When determining the percentage of candidates voted for on a ballot, it is rounded up to the next highest integer from 0.5. Ballots that do not have at least half of the candidates ranked are not considered in an election.
Assigned Person(s): | Justin
Unique Task Name: | Invalid Ballots Testing
Associated User Story: | IRV Candidate Rankings Filled in Ballot
Short Description: | Testing for ballot invalidation.
Additional Notes: | None
Assumptions: | None
Acceptance Criteria: | All tests pass and accpetance critieria for the IRV candidate rankings filled in ballot PBI is fulfilled. Test logs are written.
Assigned Person(s): | Justin
Unique Task Name: | PO CSV Input Coding
Associated User Story: | PO Algorithm CSV Input
Short Description: | Popularity election where a single winner is determined based on the candidate receiving the most ballots with a fair coin toss if there is a tie or ties between candidates.
Additional Notes: | None
Assumptions: | There is at least one candidate in the election
Acceptance Criteria: | The candidate with the most number of ballots wins the election. If there is a tie for the most number of votes, a fair coin flip should determine the winner. A media file is created to the current directory that has PO stats and information about the election so that the winner can be announced by the media. An audi file of the election is created to the current directory so the election can be validated. PO election ballots are brought in via a .csv file that is formatted the same way as the example in the writeup. 1st line: “PO” for Popularity Only 2nd Line: Number of Candidates 3rd Line: The candidates and their party in []. Name and party are separated by commas. 4th LIne: Number of Ballots 5th Line on: A single ballot vote for a single candidate candidate
Assigned Person(s): | Noah
Unique Task Name: | PO CSV Input Testing
Associated User Story: | PO Algorithm CSV Input
Short Description: | Tests the PO CSV Input Coding to ensure it works as intended
Additional Notes: | None
Assumptions: | There is at least one candidate in the election
Acceptance Criteria: | All tests pass and the acceptance criteria for PO CSV Input Coding are fulfilled
Assigned Person(s): | Noah
Unique Task Name: | Invalidated Ballots File Coding
Associated User Story: | Invalidated Ballots File
Short Description: | Create a function that takes in a list of invalidated ballots and prints them to a file
Additional Notes: | File named invalidated_dateofelection.xxx
Assumptions: | The invalidated ballots have been correctly identified and stored
Acceptance Criteria: | A file named invalidated_dateofelection.xxx that contains a listing of the invalidated ballots is created. Only invalidated ballots are contained in the file. The ballots are separate and readable.
Assigned Person(s): | Mohammad
Unique Task Name: | Invalidated Ballots File Testing
Associated User Story: | Invalidated Ballots File
Short Description: | Create unit tests to test the invalidated ballots code
Additional Notes: | None
Assumptions: | None
Acceptance Criteria: | Test cases with adequate coverage have been created and passed. The associated test logs are created
Assigned Person(s): | Mohammad

## Input Multiple Files PBI
Name: | Input multiple files | Associated Tasks:
Priority: | 1 | OPL Multiple Input Files Coding
Description: | As an Election Official, I want to be able to account for ballots from different polling locations, So that each ballot from each polling location can be counted towards the election | IR Multiple Input Files Coding
Acceptance Criteria: | Multiple CSV files should be able to be inserted into the ballot file Each CSV file can be inserted in any order Each CSV file is processed | OPL Multiple Input Files Testing
Definition of Done: | Passes all regression tests Passes testing per acceptance criteria items Documentation (i.e., JavaDocs) for the feature has been completed Able to show in feature demo | IR Multiple Input Files Testing
Effort: | Medium
PBI Author(s): | John Foley

## IRV candidate rankings filled i
Name: | IRV candidate rankings filled in ballot | Associated Tasks:
Priority: | 2 | Invalid Ballots Coding
Description: | As an election official, I want to have ballots be invalidated because the state election officials have mandated that ballots with less than half of the candidates ranked must be removed from the election. | Invalid Ballots Testing
Acceptance Criteria: | When determining the percentage of candidates voted for on a ballot, it is rounded up to the next highest integer from 0.5. Ballots that do not have at least half of the candidates ranked are not considered in an election.
Definition of Done: | Passes all regression tests Passes testing per acceptance criteria items Documentation (i.e., JavaDocs) for the feature has been completed Able to show feature in demo
Effort: | Small
PBI Author(s): | Justin Lam

## Invalidated ballots file PBI
Name: | Invalidated ballots file | Associated Tasks:
Priority: | 4 | PO CSV Input Coding
Description: | As an election official, I want to be able to see the ballots that have been invalidated so I can ensure a fair election. | PO CSV Input Testing
Acceptance Criteria: | A file named invalidated_dateofelection.xxx that contains a listing of the invalidated ballots is created. Only invalidated ballots are contained in the file. The ballots are separate and readable.
Definition of Done: | Passes all regression tests Passes testing per acceptance criteria items Documentation (i.e., JavaDocs) for the feature has been completed Able to show feature in demo
Effort: | Small
PBI Author(s): | Justin Lam

## PO Algorithm CSV Input PBI
Name: | PO Algorithm CSV Input | Associated Tasks:
Priority: | 3 | Invalidated Ballots File Coding
Description: | As an election official, I want the system to be able to take in PO ballots, so that the program can quickly determine the results of the election. | Invalidated Ballots File Testing
Acceptance Criteria: | PO election ballots are brought in via a .csv file that is formatted the same way as the example in the writeup. 1st line: “PO” for Popularity Only 2nd Line: Number of Candidates 3rd Line: The candidates and their party in []. Name and party are separated by commas. 4th LIne: Number of Ballots 5th Line on: A single ballot vote for a single candidate candidate
Definition of Done: | Passes all regression tests Passes testing per acceptance criteria items Documentation (i.e., JavaDocs) for the feature has been completed Able to show feature in demo
Effort: | Medium
PBI Author(s): | Michael Markiewicz